## Slide 1: Health systems effects of EHN Projects Pakistan and Sudan An embedded retrospective case study analysis of Pakistan and Sudan

## Slide 2: INTRODUCTION
Methods
Context
Findings
Conclusion

## Slide 3: Aims of Study
To learn about
Opportunities taken and opportunities lost for strengthening systems through SC EHN projects
Sudan and Pakistan over the last 7 years.
To develop recommendations
Provide lessons learned and inform global development thinking on improving the strengthening of systems for health-capacity, sustainability, and resilience - while responding to the immediate health needs required in emergencies.

## Slide 4: Introduction
Methods
Systematic, embedded, multiple case study design
      Theory development through a review of the literature
      Case selection, 1 project in Pakistan from 2011 to 2018 from the two regions and different emergencies and a number of projects from Sudan from Darfur and S. Kordofan from 2013 to 2018.
      Data collection by case, (reviewed 13 documents from Sudan (Darfur & Kordofan and a number of them from Pakistan)
      Data analysis by case, using a codebook with eight themes, 20 sub-themes, and 19 explanatory propositions and Nvivo for Sudan and Pakistan
      individual case report writing
      country case report writing
      country case report review and key informant interviews,
      cross-country analysis

## Slide 5: RESULTS Country context Findings – country case studies Findings – cross country analysis

## Slide 6: Country context
Sudan:
    Darfur – conflict and unrest
    S Kordofan – political unrest and conflict
    A number of OFDA projects
Pakistan:
Afghan refugees in the KPK province.
IDPs due to floods in the Sindh province
Funding for Pakistan: $2.9 million (Phase I), $4.6 million (Phase II), and $3.4 million (Phase III).

## Slide 7: Emergency Health & Nutrition Projects
EHN projects are heavily determined by:
Externally driven events and crises (political, economic, natural events and disasters)
Multiplicity of actors from donors to implementers
National systems either weak, or lacking coherence, or both
Often large funding, coming in discrete short frames
Focus on life saving interventions

## Slide 8: EHN Case Study Findings
Sudan
Effort to integrate emergency services into the health system are visible:
Health facilities were handed over after upgrade
New health facilities were added to the health system; with added federal budget for these.
Health facility systems, Capacity building and Task shifting
Community based platforms
MOH ownership of quality service through the system
Influence on protocol and policy

## Slide 9: EHN Case Study Findings
Pakistan
Effort to integrate emergency services into the health system are visible:
Health facilities deliberately worked to reach the most difficult to reach – refugees and IDPs
Health facility systems
Capacity building and Task shifting
Community engagement
Integration into the PWD / FP2020/ CIP
Influence on protocol and policy

## Slide 10: EHN Case Study Analysis
1. EHN project design and reporting
        Project reporting and documentation system is not inclined towards capturing system contributions.
        Project designs are always based on life saving interventions – same design continues from a funding phase to another.
2. EHN projects are implemented with contextual adaptation
Project reporting does not capture the adaptation
Processes and learning how activities were implemented are not the focus – Reach/ target is the focus

## Slide 11: The Binkerhoff Model

## Slide 12: EHN Case Study Analysis
3. MOH (when present) relationships aim to facilitate project implementation and not influence or contribute to the health system
        Usually MOH involvement is restricted to sharing information and some involvement at the activity level.
        Not much done to ensure participation with an aim to review or strengthen the system
4. Community engagement also aims for project facilitation
Community groups and forums are for information sharing and messaging
Community involvement for decision making is limited

## Slide 13: Conclusions
There is a need to document processes along the lines of the sub themes and explanatory prepositions to understand details
Involve further the different stake holders including the community to understand whether the program messages were widely understood and accepted
Different way of program design and project proposals ???
We CAN Save Lives and strengthen a system!