## Instructions
Health and Nutrition Service Delivery Exit Tool Version 5
Purpose
The purpose of this tool is to create clear exit indicators, promote regular monitoring and visualize readiness in efforts to transition from humanitarian to routine health and nutrition services through governmental, developmental or other service providers. The data from this tool allows for comparison of key customized indicators over selected timeframes to guide future actions. The tool can be used for monitoring transition at multiple levels--deciding on readiness for exiting individual clinics (mobile or fixed), geographic program locations or even at overall national program level. The timeframes for tracking can also be customized; from weekly or biweekly for an outbreak to monthly in a three-month rapid response mechanism intervention. Fixed locations in chronic complex emergencies may choose to reassess progress towards transitioning on a quarterly basis.
Who could use this tool?
This tool is for use by stakeholders who implement humanitarian interventions. The purpose of this tool is to aid in developing and monitoring their health and nutrition exit strategy and transition readiness over customizable periods of time--weeks, months, quarters. The tool can be shared and adapted for community leaders, ministries of health and other government officials, health or nutrition clusters, local or international NGOs, donors and others. Results should be shared amongst key stakeholders. Note: the spider diagram template visualizations and instructions work best in later versions of Excel such as in Office 365.
What are spider diagrams?
Spider diagrams also called radar charts are used for data visualization from tables. They allow data to be aggregated on a common scale or axis and compared. In this tool readiness for exit is assessed on a scale from 0 to 5 (red line) with 5 being the exit target and compared to baseline (green line) and targets (blue line) over time. The closer the current indicator scoring (red line) is to 5 and the edge of the spider web (the target line in blue), the more ready for transitioning the program or clinic is based on the key exit indicators chosen. See outbreak example tab.
What are the recommended steps for using the tool and creating the visualizations in the Spider Diagram Template tab?
1. Gather your strategy team: although the tool can be used by one person, it is recommended that those involved in transitioning a clinic, intervention site or program meet with the relevant stakeholders to agree on the key exit indicators and targets that the intervention is aiming to achieve and by when. Advocate with stakeholders to agree on a complete exit or handing over service delivery to another partner (i.e. community, ministry, developmental actor, etc.)
2. Select and describe exit indicators: From the Exit Indicator Menu spreadsheet tab, select 5 to 10 maximum exit indicator categories (column B) and indicator descriptions (column C) that are relevant to your humanitarian intervention (s).
- Paste the indicator categories and descriptions into the Spider Diagram Template in columns 1 and 2.
- Select at least 5 categories and no more than 10 categories.
- Review and customize the indicator definitions to fit your context and timeframes. If there are indicators that are more important or specific for your intervention transition feel free to add custom indicators in as well. You are not restricted to the Exit Indicator Menu examples.
- If you would like to combine several indicators into a category--just be careful to modify the excel formulas so the visualizations still work or ask for help.
Note: exit indicators are similar to but not the same as all program indicators. They should be very high level indicators that you think are so important that you should not plan exiting or transitioning out of service delivery if not achieved. For example exclusive breastfeeding prevalence is an important indicator in many of our projects; however, it is unlikely in a humanitarian situation that an organization would not exit if the prevalence of exclusive breastfeeding was low.
3. Define a target for each indicator and type it into the exit readiness criteria section 3 column D. This should be what you will consider an indicator score of 5.
4. Define your exit indicator scoring (section 4): Decide on how you will score readiness for each indicator selected with a score of 5 being your target exit criteria (defined in step 3 above) and enter the quantitative values (numbers or %) or descriptions if more qualitative in the indicator scoring section 5.
- For numerical or % values this will be easier.
- For more qualitative indicators it will take more time initially to define on the scale of 1 to 5.
5. Choose your monitoring timeframe: In row 8 of section 5 under the Achievement Timeframe--from the drop down menus choose a timeframe for reassessing your progress based on the intervention-- weekly, monthly or quarterly. In the completed outbreak example given on the last tab, weekly monitoring was chosen--Week 1 Achieved, Week 2 Achieved...
6. Calculate and record your baseline: Based on the indicator scoring that you defined from 1 to 5 in section 4, calculate your baseline from 1 to 5 (with 5 being the best--your exit target) so your progress can be monitored.
- Enter your values (1 to 5) for each indicator in the "Baseline" column of the Spider Diagram template.
- Enter the date of the baseline assessment or review in cell J8.
- If you input less than 10 categories in the table for baseline and results your spider diagrams will have gaps and look distorted. Follow the instructions on excel tips in the template to fix this.
7. Ongoing monitoring: At your initially planned time periods (which you can change), reassess and rescore your exit indicators and enter those indicator scores (from 1 to 5) in the relevant timeframe column and the spider diagram for that time period will be created. With the template you can reassess and compare up to 4 points in time.
8. Exiting analysis: Review and discuss the following questions with relevant stakeholders using the results from the spider diagrams.
  a. Are you close to your predefined targets (5) in all categories and should prepare for transition?
  b. What corrective actions are needed, if any? Are there areas scoring low that require extra program emphasis to improve readiness?
  c. Is the exit/transition plan and timeframe realistic if not near your exit target for most critical areas?
  d. What should the stakeholders prioritize over the next monitoring period?
  e. What action steps are needed by whom and when to be able to exit responsibly as initially planned?
  f. Who would it be helpful to share these exit monitoring results with?
  g. Which factors affecting exit are beyond your control?
  Note: it is not expected that a score of "5" will be needed for all indicators in order to transition successfully, but if these are critical exit indicators than the majority should be achieved as far as the decision to exit lies with the implementing stakeholders.
What if I have questions?
Every humanitarian context is different. Exit indicators and definitions need to be customizable and defined for the local setting. If you are not sure which indicators and definitions are needed, please check with the relevant country level sector advisor. If still not clear or you have technical issues with the spreadsheet or your version of Excel, please write to the responsible GSO health and nutrition advisor—currently wendy.dyment@medair.org and copy in your country level health and nutrition advisor so they are also aware and we can further improve the tool.

## Exit Indicator Menu
Customizable Exit Indicator Examples Menu
Public Health Emergency Intervention Type | Exit Indicator/Category--Label | Indicator Description Examples
A. General
| Security Incidents | # and severity of security incidents over the last 3 months (Target Example: No ongoing security incidents with protection issues)
| Population Movements | Returnees or IDPs entering or fleeing the area (Target Example: None)
| Financial Capacity | Agriculturalist population has access to fields and 1 full planting/harvest cycle of good yield
| Market Function | Markets open with products and pricing as before the crisis and functioning normally
| Potential Sustainability | Health system functional and adequately resourced (funding,HR) for response needed
| Beneficiary Needs | All basic subsistence needs have been met (COMPAS)
| Exit Plan | Handover plans and timelines with community, Ministry of Health, and other relevant stakeholders such as local or international NGOs developed and agreed
| Public Health Emergency Trend | The public health emergency (nutritional, displacement, outbreak) is controlled and not anticipated to worsen over the coming 3 months
| Communities | Regular consultation and plan developed with community leaders over transition and date for handover of services
| Timeframe | Transition planning discussions with handover partner, community, relevant ministries and donors started at least 3-6 months before planned exit
| Developmental Funding | Developmental donors with ongoing development or transitional funding mechanisms established
B. Primary Health Care (PHC)
Partner | PHC Sustainability | PHC system functional and adequately resourced by nonMedair actors (funding,HR) for PHC response needed
Service delivery | Services | PHC services restablished and at or above precrisis level
| Sphere | Sphere minimums for health service delivery achieved
| Triage | Triage in place at health site registration area. Staff trained on recognising danger signs and IMCI
RH Specific | ANC Quality | 80% of ANC record cards on audit completed correctly
| Delivery Quality | % of deliveries with corrrect use of partograms
| Obstetric Referrals | System for emergency obstetric referrals established and well-functioning
Quality | Measles Coverage | % of children aged 6 months to 15 years vaccinated against measles (Target ≥95%) (Sphere)
| Supervision | Handover partner active in quality supervision with at least monthly site visits
| Quality of Treatment | % of patients treated correctly as per national or global guidelines based on exit interviews and/or patient record audits
| IMCI Quality | % of children U5 treated as per national IMCI guidelines based on exit interviews
| Consultations/Clinician/d | Average number of total consultations (new and repeat cases) seen by each clinician per day. Calculation: (Total # of consultations in 1 wk)/(# of FTE clinicians in health facility)÷(# of days HF open per week) <Sphere>
Referrals | Obstetric Referrals | System for emergency obstetric referrals established and well-functioning
| Referrals | System for emergency medical referrals established and well-functioning
Statistics | Crude Mortality Rate | The rate of death in the entire population, including both women and men and all ages is <1/10,000 persons/day or returns to precrisis regional baselines. Calculation: <Total # of deaths in time period/(midperiod pop. X # of days in time period) >*10,000 persons= deaths/10,000 persons/day (Sphere)
| Under Five Mortality Rate | The rate of death among children below five years of age in the population is < 2/10,000 children U5/d or returns to precrisis regional baselines. Calculation: <Total # of deaths in U5 in time period/(total # of U5 X # of days in time period) >*10,000 persons= deaths/10,000 U5 /day (Sphere)
| Maternal Mortality Ratio | The number of maternal deaths per 100,000 live births. (WHO) Maternal death= the death of a woman while pregnant or within 42 days of termination of pregnancy, irrespective of the duration and the site of the pregnancy, and can stem from any cause related to or aggravated by the pregnancy or its management, but not from accidental or incidental causes. Maternal mortality ratio calculation: # of maternal deaths over a period of time (usually 1 year) x 100,000/Total # of live births occuring within the reference period (usually 1 year) (Measure)
| Neonatal Mortality Rate | The # of neonatal deaths per 1000 live births. Neonatal death is defined as a death during the first 28 days of life. Calculation: (# neonatal deaths x 1000)/Total # of live births (Measure)
Access | Clinic Utilisation Rate | The # of new outpatient consultations per person per year. Target: >2-4 new consultations/person/year among disaster affected population (Sphere)
| Mobile Clinics or Outreaches | Clinics seeing < 20 patients/day and/or access to services within a reasonable distance
| Geographic Access | % of population able to access PHC within one hour's walk from dwellings (Sphere)
Supply chain | Drug supply chain | Drug supply system in place with 2-3 months buffer stock and without current NGO assistance needed
Prevention | LLIN Usage | % of U5 and PLW's in malaria endemic areas reporting LLIN usage
Community | Community Oversight | Local health committees established and involved in health service quality oversight
WASH | Clinic Waste Mgmt | Clinic waste management system in place and operational
| IPC | IPC minimum standards achieved at health sites including staff trained, supervised and protocols in place
NCD Specific | NCD Training | NCD training on prevention and management of hypertension, asthma, diabetes provided to clinicans and nurses
| NCD Drugs | NCD medicines and 2 months buffer stock available in clinic
| NCD Referrals | Caseload documented and referred to PHCC providing NCD and patient notes handed over
Health workforce | HR | Minimum recommended staffing as per national guidelines available, trained and engaged in supervision
MHPSS | mhGAP HIG | Relevant staff trained, effective carrying out group sessions and referral systems established
C. Nutritional Emergency
See also Indicators above as many in general and health are also relevant for nutrition programming
| GAM Rate | GAM: The % of children ages 6 to 59 months with a weight for height less than 80% of the median weight of children with the same height in the reference population, and/or suffering from oedema. Target: GAM < 15% or <10%without aggravating factors.
| Coverage | The # of individuals receiving treatment as a proportion of the # of people that need treatment. (Can be disaggregated by SAM and MAM). Target: >50% rural, >70% urban, >90% formal camps (Sphere)
| Outcomes | CMAM program discharge outcome indicators in line with Sphere minimum standards for recovered, died and defaulted
| Program Quality | ≥ 85% score on Medair CMAM supervision checklist
| Patient Care | ≥85% of patients treated as per national protocol on monthly nutrition card audits by projects end
| Partner Capacity | Local health partner with sufficient capacity (funding,HR) and staff trained on CMAM management and achieving >85% on CMAM supervision checklist
| Funding | Handover partner with confirmed ongoing funding to support minimum standards nutrition intervention needed
| HR Ratios | CMAM staffing levels meet minimum staff to beneficiary ratios with at least one staff member able to diagnose, classify and treat coexisting illnesses per nutrition site
| Supply Chain | Handover partner has sufficient nutritional supplies, 2 month buffer, and requisite nutrition supply chain agreements for future nutritional products x 6 months
| Stockouts | No stockouts of nutrition supplies, admission drugs or coexisting illness treatment drugs in past month
| Expected GAM Trend | Nutritional situation including GAM rate is not projected to worsen over the next 3 months
| Seasonal deterioration | No deterioration of the nutritional situation is anticipated i.e. seasonal deterioration (IASC)
| IYCF-E | Percentage of caregivers who have access to timely, appropriate, nutritionally adequate and safe complementary foods for children aged 6 to 23 months (Sphere)
| Community Nutrition Support | Community structures exist to support continuum of nutrition care and maternal support (e.g. Mother support groups)
| Community Mobilization System | A system for supporting outreach, active case finding, referral, defaulter tracing and follow-up established and achieving Sphere minimums for coverage with a minimum of 1 outreach worker: 500 population (Sphere)
| Quality | Over X% score on CMAM supervision checklist including minimum WASH in facility
| HR | Minimum recommended staffing as per national guidelines available, trained and supervised
| IPC Trends | Integrated Food Security Classification (IPC) Phase 3 Crisis or below and not projected to increase to Emergency or Famine phase (4, 5) over the next 3-6 months
| Integration | Nutrition services integrated into health clinics (screening, treatment, and vaccination )
| Referrals | Bidirectional referral system between all CMAM elements developed and operational (community, SC, OTP, TSFP)
| SAM Caseload | < 30 SAM patients in program (ENN)
| MAM Caseload | < 30 TSFP patients (IASC)
| Communicable diseases | Control measures for infectious disease are effective (IASC)
| Childhood Morbidity | Stable incidence/low levels of illness and no outbreak diseases (GNC MAM Decision Tool)
| Displacement | No significant population displacement or no increase in displacement or sparsely populated area (GNC MAM Decision Tool)
| GFD | General food distribution is adequate (general ration ≥2100kca/person/day) and meeting planned nutritional requirements (IASC)
D. Outbreak
| Case Fatality Rate | CFR reaches is below expected threshold for the outbreak disease. Definition:The # of people who die of a disease over a set period of time divided by the # of people who have the disease over a set period of time *100 = X % (Sphere)
| Case Management Quality | Standard protocols for case management exist with X % adherence on supervision checklists
| Health System Capacity for Management | Existing health system has trained staff and resourced to manage current and projected future caseloads
| Surveillance System | System established and ≥90% of alerts reported within 24 hours
| Outbreak Prevention | Community SBCC systems established and X % population reached with info on outbreak disease related risk, prevention activities and recommended health seeking
| Vaccination coverage | % of eligable population vaccinated against outbreak disease at or above % needed for herd immunity
| Supply Chain | Handover partner has sufficient supply chain system in place and outbreak response supplies in place
| WASH capacity | For WASH related outbreaks--system in place to prevent future outbreaks (such as access to clean water)
| Outbreak Thresholds | Current number of disease cases below country's outbreak threshold
| IPC | IPC minimum standards achieved at health sites including staff trained, supervised and protocols in place
| Outbreak referrals | Safe referral system established and operational for suspected or confirmed outbreak cases
E. Population Displacement
See Indicators above as most are also relevant for population displacement
| Health System Capacity for Management | Health system functional and adequately resourced (funding,HR) for IDP/refugee response needed
| Clinic Utilisation Rate | The # of new outpatient consultations per person per year. Target: >2-4 new consultations/person/year among disaster affected population (Sphere)
| Quality of Treatment | % of patients treated correctly as per national or global guidelines based on exit interviews and/or patient record audits
| Population Movements | No ongoing returnees or IDPs entering or fleeing the area
| Access | % of population able to access PHC within one hour's walk from dwellings (Sphere)
| Financial access | % of population able to financially access PHC services

## Spider Diagram Template
|  |  |  | 4.Indicator Scoring |  |  |  |  | Baseline |  | 5. Achievement Timeframe
| 1. Exit Indicator Category | 2. Indicator description | 3. Target Criteria for Exit Readiness | 1 | 2 | 3 | 4 | 5 | Date Assessed: ___/____/____ | Target | Week 1 Achieved | Month 2 Achieved | Q3 Achieved | Week 4 Achieved | Week 1 Achieved | Month 1 Achieved | Q1 Achieved
1 | [9 empty] | 5 |  |  |  |  | Week 2 Achieved | Month 2 Achieved | Q2 Achieved
2 | [9 empty] | 5 |  |  |  |  | Week 3 Achieved | Month 3 Achieved | Q3 Achieved
3 | [9 empty] | 5 |  |  |  |  | Week 4 Achieved | Month 4 Achieved | Q4 Achieved
4 | [9 empty] | 5
5 | [9 empty] | 5
6 | [9 empty] | 5
7 | [9 empty] | 5
8 | [9 empty] | 5
9 | [9 empty] | 5
10 | [9 empty] | 5
Excel Tips that work for recent versions of Excel: If you select less than 10 indicator categories (section 1--less than all of the 10 rows used), after you finish entering your achievement results for a time period in section 5 (any of columns L-O) , your spider diagram will have gaps and not look correct. To fix this do the following: Click on the relevant titled chart for the results you just entered. Click on the filter icon to the right of the diagram (3rd box down). Select Values tab (not Name). Scroll down to the Categories section and unclick if needed (Select All). Then manually select by clicking the boxes all the names of your categories in section 1 and ensure no other boxes are selected. This will make a spider diagram with the correct number of sides, and no gaps for the number of categories you have selected to monitor for exiting.

## Outbreak example
|  |  |  | 4. Indicator Scoring |  |  |  |  | Baseline |  | 5. Achievement Timeframe
| 1. Exit Indicator Category | 2. Indicator description | 3. Target Criteria for Exit Readiness | 1 | 2 | 3 | 4 | 5 | Date Assessed: __10_/__2__/__2019__ | Target | Week 1 Achieved | Week 2 Achieved | Week 3 Achieved | Week 4 Achieved | Week 1 Achieved | Month 1 Achieved | Q1 Achieved
1 | Case fatality rate | % of reported cases of cholera which are fatal in the last week | <1% cholera case fatality rate at supported sites | ≥ 4% cholera CFR | 3-<4% cholera CFR | 2-<3% cholera CFR | 1-<2% cholera CFR | <1% cholera CFR | 1 | 5 | 1 | 1 | 3 | 4 | Week 2 Achieved | Month 2 Achieved | Q2 Achieved
2 | Case management quality | Standard protocols for cholera case management exists with >85% adherence on weekly conducted supervision checklists | >85% adherence on weekly cholera case management supervision checklists | <70% | >70% | >75% | >80% | >85% | 1 | 5 | 1 | 2 | 3 | 5 | Week 3 Achieved | Month 3 Achieved | Q3 Achieved
3 | Health system capacity | Existing health system has trained staff and resourced to manage current caseloads | >90% of relevant staff trained and resourced to manage current case load with appropriate clinician to patient ratios at supported sites (Sphere < 50 consultations/clinician/day) | <60% relevant staff trained=0 points | >60% of relevant staff trained=1 point | >70% of relevant staff trained=1.5 points | >80% of relevant staff trained=2 points | >90% of relevant staff trained=2.5 points | 1.5 | 5 | 3.5 | 3.5 | 5 | 5 | Week 4 Achieved | Month 4 Achieved | Q4 Achieved
|  |  |  | Caseload > 70 AWD consultations/clinician per day= 0 points | Caseload 65-70 AWD consultations/clinician per day - 1 point | Caseload 60-65 AWD consultations/clinician per day = 1.5 | Caseload 55-60 AWD consultations/clinician per day= 2 points | Caseload < 50 AWD consultations/clinician per day = 2.5 points
4 | Surveillance system | System established and ≥90% of alerts reported within 24 hours | ≥90% alerts reported within 24 hours | <60% AWD alerts reported within 24 hours | >60% AWD alerts reported within 24 hours | >70% AWD alerts reported within 24 hours | >80% AWD alerts reported within 24 hours | >90% AWD alerts reported within 24 hours | 1 | 5 | 1 | 1 | 4 | 5
5 | Prevention | Community SBCC systems established and over 90 % population reached with info on outbreak disease related risk, prevention activities and recommended health seeking | >90% population reached with info on cholera related risk, prevention activities and recommended health seeking | <75% target population reached with SBCC on cholera | >75% target population reached with SBCC on cholera | >80% target population reached with SBCC on cholera | >85% target population reached with SBCC on cholera | >90% target population reached with SBCC on cholera | 1 | 5 | 2 | 2 | 3 | 5
6 | Vaccination Coverage | % of target popuation age ≥ 1 yo receiving 2 doses of OCV in mass campaign on coverage survey | ≥85% of of target population age ≥ 1 yo receiving 2 doses of OCV in mass campaign in coverage survey | <70% coverage | ≥70% coverage | ≥75% coverage | ≥80% coverage | ≥85% coverage | 1 | 5 | 1 | 1 | 1 | 4
7 | [9 empty] | 5
8 | [9 empty] | 5
9 | [9 empty] | 5
10 | [9 empty] | 5
Excel Tips: If you select less than 10 indicator categories (section 1--less than all of the 10 rows used), after you finish entering your achievement results for a time period in section 5 (any of columns L-O) , your spider diagram will have gaps and not look correct. To fix this do the following: Click on the relevant titled chart for the results you just entered. Click on the filter icon to the right of the diagram (3rd box down). Select Values tab (not Name). Scroll down to the Categories section and unclick if needed (Select All). Then manually select by clicking the boxes all the names of your categories in section 1 and ensure no other boxes are selected. This will make a spider diagram with the correct number of sides, and no gaps for the number of categories you have selected to monitor for exiting.
Description: In week 1 we see some progress in health system capacity--getting staff and improving on staff to patient ratios but nowhere near the minimum Sphere standards yet. Prevention too is increasing and more people are being reached with messaging since the start of the intervention but again with better coveage needed. No progress is yet seen on the case fatality rate, vaccination coverage, surveillance reporting or case management quality and the implementing team will need to continue to focus on all key areas.
Description: In week 2 of the outbreak response we see improved quality of case management after training and supportive supervision but still not at targeted indicator goals for transitioning and still need to improve on the case fatality rate and prevention including vaccination and surviellance system. Intervention team needs to continue focusing on all exit indicator category areas for improvement.
Description: In week 3 of the outbreak response we see some continued improvement on case management quality but marked improvement in prevention, surveillance and the health system capacity to respond as well as some improvement with lowering case fatality rates; however, all except health system capacity are still not at the level targeted for transitioning out of the response. Achieving the case fatality rate is especially critical and doing an OCV campaign and getting sufficient coverage rates still needs to be finalized while continuing to expand on prevention activities, and further strengthen the surveillance systems and case management quality.
Description: By week 4 of the intervention case management quality is at the desired level in this example with over 85% achievement on a cholera quality of care supervision checklist. The surveillance system is operational and reporting over 90% of alerts wtihin 24 hours, over 90% of the targeted population has been reached with prevention messaging, and the health system has over 90% of the recommended staff and are staffed at Sphere minimum standards for their caseloads. Vaccination coverage has markedly improved over this week with a continuing campaign; however, the implementing team has not yet reached 85% of the population with 2 doses and the case fatality rate although improved is still not at globally acceptable standards of <1 % CFR for cholera. So although having reached many of the exit indicator targets, the implementing team will need to continue to intervene and further monitor until vaccination coverage and the case fatality rate reach global standards.
Note on K8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The target should always be 5 here